## CTF timeline 2026-27
CTF Timeline for for Proposals beginning in AY 2026-27
Company name
Project lead
Project start date: | 2025-11-12 |  |  |  | 2025 | [17 empty] | 2026 | [34 empty] | Start of new AY
[5 empty] | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | 2026-27
|  |  |  | w/c | 1899-12-31 | 1900-01-07 | 1900-01-14 | 1900-01-21 | 1900-01-28 | 1900-01-05 | 1900-01-12 | 1900-01-19 | 1900-01-26 | 1900-01-02 | 1900-01-09 | 1900-01-16 | 1900-01-23 | 1899-12-31 | 1900-01-07 | 1900-01-14 | 1900-01-21 | 1900-01-28 | 1900-01-04 | 1900-01-11 | 1900-01-18 | 1900-01-25 | 1900-01-01 | 1900-01-08 | 1900-01-15 | 1900-01-22 | 1900-01-01 | 1900-01-08 | 1900-01-15 | 1900-01-22 | 1900-01-29 | 1900-01-05 | 1900-01-12 | 1900-01-19 | 1900-01-26 | 1900-01-03 | 1900-01-10 | 1900-01-17 | 1900-01-24 | 1899-12-31 | 1900-01-07 | 1900-01-14 | 1900-01-21 | 1900-01-28 | 1900-01-05 | 1900-01-12 | 1900-01-19 | 1900-01-26 | 1900-01-02 | 1900-01-09 | 1900-01-16 | 1900-01-23 | 1900-01-30
Milestone description | - | w/c | Weeks |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53
Stage 1
Invitation for Expressions of Interest |  | 2025-11-12 | 3 | bar: W11 to W13
Deadline for EOIs |  | 2025-11-28 | 1 | bar: W13
Stage 2
Applications being worked up |  | 2025-12-17 | 8 | bar: W16 to W23
Deadline for applications |  | 2026-02-06 | 1 | bar: W23
SFC/College liaison around plans |  | 2026-02-09 | 10 | bar: W24 to W33
Final response to college |  | 2025-04-20 | 1 | bar: W17; W34
Stage 3
FinCo meeting - approval |  | 2026-04-30 | 1 |  | W35: 30
Board meeting |  | 2026-05-14 | 1 |  | W37: 14
Board approval |  | 2026-05-14 | 2 | bar: W37 to W38
Stage 4
Colleges commence CTF activities |  | 2026-06-01 | bar: W40 to W53
Stage 5
Pre-term engagement SFC - College |  | 2026-06-01 | bar: W42 to W53
Note: This timetable may be subject to revision depending on budget announcement on 13 January 2026.