## Slide 1: Workshop 2 The Preferred Way Forward
SCIM for tertiary education institutions
Strategic Outline Case (SOC)

## Slide 2: Slide Guide
Colour Coding | Description
 | Workshop Slides
 | Facilitator notes and preparation
 | Templates for workshop exercises with key stakeholders and support development of five cases.

## Slide 3: Workshop 2 The Preferred Way Forward Workshop Pre Work
Evidence and documentation:
Circulate the Case for Change outputs
Provide the draft longlist of options
Provide CSFs, constraints, dependencies, and strategic alignment summary
Provide any technical studies, feasibility reports, or demand/asset data
Provide financial baseline and affordability envelope
Stakeholder preparation:
Ask attendees to review the longlist and identify:
Options they believe are viable
Options that clearly fail CSFs
Missing options or variations
Ask finance and commercial leads to prepare early views on:
Affordability
Procurement feasibility
Market capacity
Revenue/capital implications

## Slide 4: SOC Workshops
SOC Case for Change,
SOC The Preferred Way Forward,
OBC Value for Money,
OBC Commercial Agreement,
OBC Management Case.

## Slide 5: Workshop 2 The Preferred Way Forward Workshop Purpose
To agree the Preferred Way Forward (PWF) by reviewing the longlist of options, applying longlist filtering criteria, and identifying a shortlist that is feasible, affordable, and strategically aligned. This workshop ensures stakeholders collectively understand the range of possible interventions, the constraints, and the emerging preferred direction before moving into detailed development.

## Slide 6: Workshop 2 The Preferred Way Forward Workshop Objectives
Option development and structuring:
Review the longlist of options generated from the Case for Change.
Ensure options reflect the Five Case Model, including service, delivery, commercial, and funding considerations.
Confirm options include Do Nothing, Do Minimum, and a range of intermediate and transformational options.
Longlist filtering:
Apply Critical Success Factors (CSFs).
Apply Green Book long list tests:
  Strategic fit.
  Value for money potential.
  Feasibility.
  Affordability.
  Deliverability.
Remove options that do not meet the CSFs or constraints.
Shortlist creation:
Agree the shortlist of viable options.
Identify the emerging Preferred Way Forward.
Confirm what further analysis is required for SOC completion.
Commercial, financial, and management considerations:
Identify early commercial implications (procurement routes, market capacity).
Identify financial constraints, revenue/capital impacts, and affordability envelope.
Identify delivery risks, dependencies, and programme implications.

## Slide 7: Workshop 2 The Preferred Way Forward Workshop Attendees
Core attendees
  Senior Responsible Owner (SRO)
  Project Sponsor / Senior Client Lead
  Project/Programme Manager
  Strategic Planning Lead
  Finance (capital & revenue)
  Service leads/operational managers
  Estates/asset management
  Procurement representative
  Commercial advisor
  Risk manager
Optional attendees
  Digital/ICT lead (if relevant to options)
  Legal advisor
  Sustainability/Net Zero lead
  External partners (local authority, NHS, regional agencies)
  Technical specialists (engineering, transport, energy, education, etc.)
  Consultants supporting business case development

## Slide 8: Workshop 2 The Preferred Way Forward Workshop Expected Outputs
Agreed longlist (validated and complete)
Filtered longlist with rationale for exclusions
Agreed shortlist of options
Identified Preferred Way Forward (or emerging PWF if further analysis required)
Option descriptions including:
  Scope
  Service model
  Delivery model
  Commercial implications
  Financial implications
  Risks, constraints, dependencies
  Benefits alignment

## Slide 9: Workshop 1 Agenda: Making the Case for Change Workshop Agenda
Welcome, Purpose & Recap of Workshop 1
Re‑statement of Strategic Context
Review of Longlist Options
Apply Critical Success Factors (CSFs) – Longlist Filtering
Shortlist Development
Defining the Preferred Way Forward
Early Economic Appraisal Inputs
Commercial, Financial & Management Case Implications
Next Steps, Actions & Responsibilities
Close

## Slide 10: Welcome, Purpose & Recap of Workshop 1
Facilitated discussion:
  What is the core problem we are trying to solve
  What evidence supports this
  What happens if we do nothing
Review of:
  Demand analysis
  Condition/capacity issues
  Risks and service pressures
Output: Agreed problem statements

## Slide 11: Re‑statement of Strategic Context
Identify expected strategic outcomes
Define benefits (quantitative and qualitative)
Link benefits to:
  National Outcomes
  Programme/organisational objectives
Prioritisation exercise
Output: Draft Benefits Register

## Slide 12: Review of Longlist Options
Review Green Book CSF categories:
  Strategic fit
  Value for money
  Commercial viability
  Financial affordability
  Achievability
Agree project‑specific CSFs
Output: SOC CSF set

## Slide 13: Apply Critical Success Factors (CSFs) – Longlist Filtering
Introduce Green Book option framework:
  Do nothing
  Do minimum
  Intermediate options
  Maximum ambition
Brainstorm longlist options
Identify options that clearly fail CSFs
Output: Initial longlist for SOC

## Slide 14: Shortlist Development
Discuss viability of remaining options
Consider:
  Deliverability
  Affordability
  Commercial feasibility
  Strategic alignment
  Risks and dependencies
Agree shortlist options to take forward to economic appraisal
Output: SOC Shortlist (typically 3–5 options)

## Slide 15: Defining the Preferred Way Forward
Review shortlist against:
  Benefits
  Risks
  Constraints
  Strategic outcomes
Identify the Preferred Way Forward (PWF) based on:
  Best strategic fit
  Best potential value for money
  Achievability within constraints
Output: Draft Preferred Way Forward narrative

## Slide 16: Early Economic Appraisal Inputs
Identify data required for SOC‑level appraisal:
  Cost ranges
  Benefits estimates
  Risk themes
  Optimism bias considerations
Confirm responsibilities for gathering evidence
Output: SOC appraisal evidence plan

## Slide 17: Commercial, Financial & Management Case Implications
Early considerations for:
  Procurement route
  Funding envelope
  Delivery model
  Governance and assurance
Capture issues to be developed in SOC drafting

## Slide 18: Next Steps, Actions & Responsibilities
Confirm drafting responsibilities for:
  Strategic Case
  Economic Case (longlist → shortlist → PWF)
  Commercial, Financial, Management inputs
Agree timeline for SOC completion and SFC submission
Confirm need for Workshop 3 (Value for Money / Economic Appraisal)

## Slide 19: Close
Recap decisions
Confirm Preferred Way Forward
Thank participants

## Slide 20: Workshop template: Critical Success Factors
Example template to use or adapt for workshop
Critical Success Factor | Description | Definition of Success
Strategic Fit |  | 
Business Needs |  | 
Value for Money |  | 
Supply Capacity |  | 
Achievability |  | 
Add other rows |  | 

## Slide 21: Workshop template: Long List
Example template to use or adapt for workshop
Long List | Solution Description and Implication
Do Nothing | 

## Slide 22: Workshop template: Long List SWOT
Example template to use or adapt for workshop
Option | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Description | Do Nothing |  |  |  |  |  |  |  | 
Strengths |  |  |  |  |  |  |  |  | 
Weaknesses |  |  |  |  |  |  |  |  | 
Opportunities |  |  |  |  |  |  |  |  | 
Threats |  |  |  |  |  |  |  |  | 
Advantages |  |  |  |  |  |  |  |  | 
Disadvantages |  |  |  |  |  |  |  |  | 
Meets investment objectives? |  |  |  |  |  |  |  |  | 
Meets CSF for Project? |  |  |  |  |  |  |  |  | 

## Slide 23: Workshop template: Option Analysis 1
Example template to use or adapt for workshop
Option | 1 | 2 | 3 | 4 | 5
Scope |  |  |  |  | 
Solution |  |  |  |  | 
Service Delivery |  |  |  |  | 
Implementation |  |  |  |  | 
Funding |  |  |  |  | 

## Slide 24: Workshop template: Option Analysis 2
Example template to use or adapt for workshop
Option | 1 | 2 | 3
Scope |  |  | 
Solution |  |  | 
Service Delivery |  |  | 
Implementation |  |  | 
Funding |  |  | 

## Slide 25: Workshop template: Preferred Way Forward
Example template to use or adapt for workshop
Option | 1
Criteria | 
Preferred Option | 
Scope | 
Solution | 
Service Delivery | 
Implementation | 

## Slide 26: Preparation for Workshop 3 Value for Money
Confirm short list and the Preferred Way Forward.
Explain long list options rejected against critical success factors (CSF).
Ensure that short listed options and strategically aligned, deliverable and affordable.
Develop detailed option specifications.
Collect cost data for economic appraisal including capital, operating and lifecycle costs including optimism bias (OB) and risk, including any assumptions.
Create a Benefits Framework.
Update Risk Register.
Risk costs ranges for sensitivity analysis.
Collect distributional and wider impacts information and data.
Economic appraisal criteria and model.
Prepare Workshop 3 materials.