## Slide 1: Workshop 4 Commercial Agreement
SCIM for Tertiary Education
Outline Business Case (OBC)

## Slide 2: Slide Guide
Colour Coding | Description
 | Workshop Slides
 | Facilitator notes and preparation
 | Templates for workshop exercises with key stakeholders and support development of five cases.

## Slide 3: Workshop 4 Commercial Case Pre Work
Review the preferred option emerging from the Economic Case.
Gather current procurement, legal, and governance constraints.
Prepare any existing market intelligence, framework options, and contracting precedents.
Bring current key risks, dependencies, and assumptions relevant to the commercial approach.

## Slide 4: OBC Workshops
SOC Case for Change.
SOC The Preferred Way Forward.
OBC Value for Money.
OBC Commercial Agreement.
OBC Management Case.

## Slide 5: Workshop 4 Commercial Case Expected Purpose
To develop the Commercial Case content for the Outline Business Case by agreeing the proposed procurement approach, commercial structure, market engagement, risk allocation, and contractual principles required to support a robust and proportionate business case.

## Slide 6: Workshop 4 Commercial Case Objectives
Confirm the commercial requirements of the preferred way forward.
Review and test feasible procurement strategy options.
Agree the preferred contracting and payment approach for OBC development.
Define proposed principles for risk allocation and market engagement.
Assign actions, owners, and evidence requirements for drafting the Commercial Case.

## Slide 7: Workshop 4 Commercial Case Attendees
Senior Responsible Owner/project sponsor.
Project manager and business case lead.
Procurement and commercial leads.
Finance representative.
Technical/estates/digital subject matter leads, as applicable.
Legal adviser, where available.
Operational or service representatives impacted by the commercial arrangement.
Governance/assurance representative, if required.

## Slide 8: Workshop 4 Commercial Case Expected Outputs
Agreed commercial principles and assumptions for the OBC.
Preferred procurement strategy and rationale.
Draft market engagement approach.
Initial commercial risk allocation matrix.
Preferred form of contract and payment mechanism assumptions.
Action log with owners and deadlines for completing the Commercial Case narrative.

## Slide 9: Workshop 4 Agenda: Commercial Agreement
Welcome, Purpose & OBC Progress Update
Strategic and Policy Context for Commercial Decisions
Preferred Way Forward – Commercial Implications
Procurement Strategy Options
Market Engagement Approach
Commercial Structure & Contracting Approach
Risk Allocation & Commercial Risk Register
Commercial Dependencies & Interfaces
Drafting Requirements for the OBC Commercial Case
Next Steps, Actions & Close

## Slide 10: Welcome, Purpose & OBC Progress Update
Recap progress across the Five Cases
Confirm Workshop 4 objectives:
  Agree commercial principles.
  Define procurement strategy.
  Clarify risk allocation.
  Shape the commercial model for the OBC.
Overview of required Commercial Case outputs for OBC submission

## Slide 11: Strategic & Policy Context for Commercial Decisions
Public Procurement (Scotland) Regulations.
Relevant Scottish policy and regulatory drivers:
  Scottish Procurement Policy Notes (SPPNs)
  Fair Work First
  Net Zero/Public Sector Climate Duties
  Community Wealth Building
Organisational procurement strategy and governance
Constraints, dependencies, and statutory considerations

## Slide 12: Preferred Way Forward – Commercial Implications
Summary of the Preferred Way Forward from the Economic Case
Commercial requirements arising from scope, scale, and delivery model
Confirm assumptions and boundaries for commercial structuring

## Slide 13: Procurement Strategy Options
Review viable procurement routes:
  Open procedure
  Restricted procedure
  Competitive procedure with negotiation
  For physical infrastructure
    Framework call‑off (e.g., SCAPE, Hub, Crown Commercial Service)
    Traditional vs Design & Build vs NEC/JCT variants
Key considerations:
  Market capacity and capability
  Complexity and innovation potential
  Timescales and risk appetite
Output: Shortlist of procurement strategy options

## Slide 14: Market Engagement Approach
Purpose and scope of market engagement
Options:
  Soft market testing
  Prior Information Notice (PIN)
  Supplier engagement events
Information required from the market
Early risks, opportunities, and supply chain insights
Output: Market engagement plan

## Slide 15: Commercial Structure and Contracting Approach
Contract form options (NEC4, JCT SBC/Q, Hub DBFM, SCAPE, etc.)
Payment mechanisms:
  Lump sum
  Target cost
  Activity‑based payments
Performance mechanisms:
  KPIs
  Service levels
  Incentives and penalties
Output: Preferred contracting approach

## Slide 16: Risk Allocation and Commercial Risk Register
Identify commercial risks:
  Design, construction, inflation, supply chain, legal/compliance
Allocate risks:
  Client‑held
  Supplier‑held
  Shared
Confirm principles for risk transfer and pricing
Output: Commercial risk allocation matrix

## Slide 17: Commercial Dependencies and Interfaces
Planning and statutory approvals
Land, title, access, utilities
Interfaces with other projects or programmes
Funding and governance dependencies
Output: Dependencies map for Commercial Case

## Slide 18: Drafting Requirements for the OBC Commercial Case
Confirm required sections:
  Procurement strategy
  Market engagement
  Risk allocation
  Contracting approach
  Commercial viability
Assign drafting responsibilities
Confirm evidence requirements and timelines

## Slide 19: Next Steps, Actions & Close
Confirm actions, owners, and deadlines
Agree timeline for OBC completion and governance review
Identify need for Workshop 5 (Management)
Close and thanks

## Slide 20: Workshop template: Commercial Principles
Example template to use or adapt for workshop.
Commercial principle 1.
Commercial principle 2.

## Slide 21: Workshop template: Capital and Revenue
Example template to use or adapt for workshop
Option | Requirement Description | £ Amt | Period (if recurring)
Capital |  |  | 
Revenue |  |  | 
Annual Maintenance |  |  | 
Lifecycle Costs |  |  | 

## Slide 22: Workshop template: Procurement Considerations
Example template to use or adapt for workshop
Option | Analysis
Market capacity and capability | 
Complexity and innovation potential | 
Timescales and risk appetite | 

## Slide 23: Workshop template: Procurement Options
Example template to use or adapt for workshop
Option | Analysis
Procedure | 
Suitable Framework | 

## Slide 24: Workshop template: Balance Sheet Treatment
Example template to use or adapt for workshop
Treatment | 1
Depreciation | 
Impairment | 
Liabilities | 
Capital Changes | 

## Slide 25: Workshop template: Stakeholder Support
Example template to use or adapt for workshop
Stakeholder | Nature of Support | Quantifiable Support
Stakeholder 1 |  | 
Stakeholder 2 |  | 
Stakeholder 3 |  | 

## Slide 26: Preparation for Workshop 5 Management Case
Finalise Commercial decisions and document the agreed approach.
Translate Commercial Outputs into delivery requirements.
Project Plan and Critical Path.
Update Risk Register.
Governance and Assurance for Project.
Finalise Benefits Register.
Contract Management Plan.