## Slide 1: Workshop 5 Management Case
SCIM for Tertiary Education
Outline Business Case (OBC)

## Slide 2: Slide Guide
Colour Coding | Description
 | Workshop Slides
 | Facilitator notes and preparation
 | Templates for workshop exercises with key stakeholders and support development of five cases.

## Slide 3: Workshop Management Case Pre Work
Document & evidence preparation.
Circulate:
Draft programme plan.
Draft governance structure.
Draft risk register.
Draft Benefits Realisation Plan.
Draft assurance plan.
Draft stakeholder engagement plan.
Updated Preferred Option summary.
Provide any technical studies, procurement strategies, or delivery constraints.
Stakeholder preparation.
Ask attendees to review and prepare comments on:
Delivery feasibility.
Resource requirements.
Risk ownership and mitigation.
Benefit ownership and measurement.
Governance and decision‑making pathways.
Ask PMO and risk leads to prepare:
Updated risk scoring.
Delivery confidence assessment.
Assurance requirements.

## Slide 4: OBC Workshops
SOC Case for Change.
SOC The Preferred Way Forward.
OBC Value for Money.
OBC Commercial Agreement.
OBC Management Case.

## Slide 5: Workshop 5 Management Case Purpose
To confirm that the project is deliverable, well‑governed, resourced, risk‑managed, and realistically planned, ensuring that the Preferred Option can be implemented successfully. This workshop validates the delivery arrangements, programme plan, risk and assurance strategy, benefits realisation approach, and governance structure required for the OBC.
The aim is to demonstrate that the project has a credible, controlled, and auditable delivery pathway aligned with SCIM and Green Book expectations.

## Slide 6: Workshop 5 Management Case Objectives
Delivery planning:
Review and agree the programme plan, milestones, critical path, and dependencies.
Confirm the delivery strategy, including phasing, enabling works, and transition planning.
Validate resource requirements (internal and external).
Governance and assurance:
Agree the governance structure, roles, responsibilities, and decision‑making pathways.
Confirm the assurance plan, including SCIM Gateway Reviews, internal audit, and external scrutiny.
Identify required approvals and reporting cycles.
Risk, issues, and dependencies.
Review the risk register, including strategic, delivery, commercial, and financial risks.
Confirm risk ownership, mitigation strategies, and contingency planning.
Validate dependencies and constraints.
Benefits realisation:
Review the Benefits Realisation Plan.
Confirm benefit owners, measurement methods, baselines, and reporting arrangements.
Ensure alignment with the Strategic Case outcomes.
Change management and readiness:
Identify organisational change requirements.
Confirm stakeholder engagement and communications approach.
Assess delivery readiness and capacity.

## Slide 7: Workshop 5 Management Case Attendees
Core attendees:
  Senior Responsible Owner (SRO)
  Project Sponsor/Senior Client Lead
  Programme/Project Manager
  Commercial/procurement advisor
  Risk manager
  Benefits manager
  Finance lead
  Service leads/operational managers
  Estates/technical delivery leads
Optional attendees:
  Legal advisor
  Digital/ICT lead (if relevant)
  HR/OD lead (for change management)
  Communications/engagement lead
  External partners (local authority, NHS, regional agencies)
  Consultants supporting programme management or delivery planning

## Slide 8: Workshop 5 Management Case Expected Outputs
Agreed governance structure with roles and responsibilities.
Updated programme plan with milestones, critical path, and dependencies.
Updated risk register with owners, mitigations, and contingency.
Updated Benefits Realisation Plan with baselines, KPIs, and benefit owners.
Delivery strategy including phasing, procurement interfaces, and transition planning.
Assurance plan including SCIM Gateway Review schedule.
Stakeholder engagement and communications plan.
Resource plan (internal and external).
Delivery readiness assessment and actions required.

## Slide 9: Workshop 5 Agenda: Management Case
Welcome, Purpose & OBC Progress Update
Strategic Context for Delivery
Delivery Model & Delivery Plan
Governance Structure
Assurance, Approvals & SCIM Requirements
Risk Management & Risk Register
Benefits Realisation Strategy
Change Management & Stakeholder Engagement
Programme Controls & Reporting
Drafting Requirements & Next Steps

## Slide 10: Welcome, Purpose & OBC Progress Update
Recap progress across the Five Cases
Confirm Workshop 5 objectives:
  Agree delivery arrangements
  Confirm governance and assurance
  Define programme controls
  Finalise Management Case inputs for the OBC
Overview of required Management Case outputs

## Slide 11: Strategic Context for Delivery
Key organisational governance requirements
SCIM expectations for delivery planning
Dependencies from Commercial and Financial Cases
Constraints affecting delivery (planning, funding, capacity)

## Slide 12: Delivery Model & Delivery Plan
Review Preferred Way Forward delivery implications
Define delivery model:
  In‑house
  Hybrid
  Supplier‑led
Develop high‑level delivery plan:
  Key milestones
  Critical path
  Stage gates
Output: Draft Delivery Plan

## Slide 13: Governance Structure
Confirm governance arrangements:
  Project Board
  Senior Responsible Owner (SRO)
  Project Manager
  Workstream leads
Decision‑making structure
Reporting lines and escalation routes
Output: Governance Structure Diagram

## Slide 14: Assurance, Approvals and SCIM Requirements
Assurance requirements:
  Gateway Reviews.
  Internal audit.
  External assurance (SFC, SG, independent reviewers).
Approvals pathway:
  SOC → OBC → FBC.
  College governance.
  SFC appraisal cycles.
Output: Assurance & Approvals Plan

## Slide 15: Risk Management & Risk Register
Review strategic and commercial risks
Identify delivery‑phase risks
Confirm risk management approach:
  Risk owner
  Mitigation strategy
  Residual risk
Link to optimism bias and contingency
Output: OBC‑level Risk Register

## Slide 16: Benefits Realisation Strategy
Review benefits identified in SOC and OBC Economic Case
Confirm:
  Benefit owners
  Measures/KPIs
  Baselines
  Tracking arrangements
Develop Benefits Realisation Plan
Output: Benefits Realisation Framework

## Slide 17: Change Management & Stakeholder Engagement
Identify key stakeholders
Engagement approach
Communications plan
Change readiness assessment
Output: Stakeholder & Change Management Plan

## Slide 18: Programme Controls & Reporting
Controls required for delivery:
  Schedule management
  Cost control
  Risk and issue management
  Quality assurance
Reporting cadence and formats
Output: Programme Controls Framework

## Slide 19: Drafting Requirements & Next Steps
Confirm required Management Case sections:
  Delivery plan
  Governance
  Assurance
  Risk management
  Benefits realisation
  Programme controls
Assign drafting responsibilities
Confirm evidence requirements and deadlines
Agree timeline for OBC completion and governance review

## Slide 20: Workshop template: Governance Structure
Example template to use or adapt for workshop
Role | Responsibilities | Decision Making
Project Board |  | 
SRO |  | 
Project Manager |  | 
Workstream Leads |  | 

## Slide 21: Workshop template: Delivery Plan
Example template to use or adapt for workshop
Plan Stage | Milestone | Dependency | Risk
Investment Decision |  |  | 
Mobilise |  |  | 
Delivery |  |  | 
Handover |  |  | 
Warranty |  |  | 
Go Live |  |  | 

## Slide 22: Workshop template: Delivery Risks
Example template to use or adapt for workshop
Delivery Stage | Risk | Mitigation

## Slide 23: Workshop template: Stakeholder Engagement
Example template to use or adapt for workshop
Stakeholder | Engagement Plan | Comms Plan | Change Readiness Assessment
Stakeholder 1 |  |  | 
Stakeholder 2 |  |  | 
Stakeholder 3 |  |  | 

## Slide 24: Workshop template: Benefit Realisation
Example template to use or adapt for workshop
Outcome | Benefit | Beneficiary | Baseline | Tracking